## README
Risk Analysis Template — How to Use This Spreadsheet
Purpose
This spreadsheet supports the risk analysis process described in the Test Analysis and Design training series. It helps your team prioritize test inventories by assessed risk and plan testing effort against available capacity. The output is a ranked, visible list of what gets tested, what gets deferred, and why.
Overview of Sheets
This workbook contains three working sheets:
Risk Analysis — This is your data entry sheet. Enter your test objectives, inventory items, likelihood and impact ratings, estimated execution hours, and any notes or rationale. Scores, priority, and rank calculate automatically.
Planning View — This sheet auto-sorts your data by effective priority (highest first) and calculates the cut-line based on your team's available capacity. You do not edit this sheet directly — it pulls everything from the Risk Analysis sheet.
Template — A blank version of the Risk Analysis sheet. Copy this tab when starting a new project or release cycle.
Getting Started
Go to the Risk Analysis sheet.
For each inventory item, enter the Objective (the broad category it belongs to), the Inventory name (the specific testable item), and Likelihood and Impact ratings using H, M, or L.
The L Score, I Score, Priority, Effective Priority, and Rank columns calculate automatically. Do not overwrite these formulas.
Optionally, enter estimated test execution hours in the Est. Hours column. These feed the capacity planning on the Planning View.
Optionally, add notes explaining the rationale for your ratings. This is especially useful during the Review and Modify step.
Understanding the Columns
Likelihood (H/M/L) — How likely is this inventory item to fail or behave incorrectly? Consider code complexity, rate of change, historical defects, whether the feature is new or mature, and integration dependencies.
Impact (H/M/L) — If this item fails, what is the impact to the user or business? Consider revenue impact, number of users affected, data integrity risk, workaround availability, and regulatory or compliance implications.
Priority — Computed automatically. Likelihood score multiplied by Impact score. High = 5, Medium = 3, Low = 1. A High likelihood and High impact item scores 25. A Low/Low item scores 1.
Adjust (+/-) — Optional manual override. Use this to bump an item's priority up or down to break ties or reflect context the formula can't capture. For example, if two items both score 9 but you know one was recently refactored and carries more risk, add +2 to that item. Only touch the rows you want to adjust — leave everything else at 0. Non-zero values are highlighted in purple so adjustments are visible.
Effective Priority — Priority plus Adjust. This is what the Planning View sorts on.
Est. Hours — Estimated test execution time for this inventory item. This is execution time only — not test design, environment setup, or defect verification. These estimates support the capacity calculation on the Planning View.
Rank — Computed automatically from Effective Priority. The item with the highest effective priority is ranked 1. Ties are broken by row order.
Using the Planning View
The Planning View has four editable input cells at the top (highlighted in amber):
# of Testers — How many testers are available for this cycle.
Hrs / Tester / Day — Effective testing hours per tester per day. This should reflect actual execution time, accounting for meetings, context switching, and other overhead. A typical value is 4-6 hours.
Start Date — First day of the testing window.
End Date — Last day of the testing window.
From these inputs, the sheet calculates available capacity in hours (testers × hours/day × business days, excluding weekends). Each inventory item's Status column is then set automatically:
Test this cycle — The item's cumulative hours fall within available capacity. This item is above the cut-line.
At capacity — This is the boundary item where cumulative hours exceed available capacity. This is where the cut-line falls.
Deferred — This item falls below the cut-line. It is not scheduled for this cycle.
To move the cut-line, change any of the four planning inputs. For example, changing the end date from June 5 to June 3 reduces available hours, and items that were previously above the cut-line will move to Deferred. You can also move the cut-line by adjusting Adjust (+/-) values on the Risk Analysis sheet to change which items rank higher.
Important Notes
Every row on the Risk Analysis sheet must have an Objective value. Do not leave the Objective column blank for items that share an objective — enter the objective name on every row. The Planning View re-sorts rows by priority, so blank objectives will appear under the wrong group.
Likelihood and Impact must be entered as a single letter: H, M, or L (uppercase). Other values will not compute correctly.
The Planning View is read-only. All edits (except the four planning inputs) should be made on the Risk Analysis sheet.
Rank values must be unique for the Planning View to work correctly. The formula handles this automatically. If you overwrite a Rank cell with a manual value, ensure no duplicates exist.
Est. Hours is optional but recommended. Without it, the capacity planning on the Planning View cannot calculate the cut-line.
Maintaining This Over Time
This analysis should be revisited when significant changes occur: new features ship, major refactoring is completed, a new release cycle begins, or customer-reported defect patterns change. Copy the Template sheet to start fresh, or update the existing Risk Analysis sheet to reflect the current state.
The Adjust (+/-) column values should be reviewed each cycle. An adjustment that made sense last release may no longer apply.

## Risk Analysis
Risk Analysis — Data Entry
Enter data here — the Planning View (Sheet 2) auto-sorts by Effective Priority and calculates the cut-line.
Based on concepts from Systematic Software Testing by Rick Craig and Stefan Jaskiel
[6 empty] | Scoring Key: | H = 5 | M = 3 | L = 1
# | Objective | Inventory | Likelihood | L Score | Impact | I Score | Priority | Adjust (+/-) | Eff. Priority | Est. Hours | Notes / Rationale | Rank
1 | Authentication | Login / Logout | H | 5 | H | 5 | 25 | 0 | 25 | 3 | Core user flow; auth provider integration | 1
2 | Authentication | Password Reset | M | 3 | M | 3 | 9 | 0 | 9 | 2 | Token-based flow; moderate complexity | 6
3 | Authentication | Session Timeout | L | 1 | M | 3 | 3 | 0 | 3 | 1 | Mature implementation; low change rate | 9
4 | Shopping Cart | Add to Cart | H | 5 | H | 5 | 25 | 0 | 25 | 3 | High traffic; frequent changes | 2
5 | Shopping Cart | Update Quantity | L | 1 | M | 3 | 3 | 0 | 3 | 1 | Simple CRUD; well-tested path | 10
6 | Shopping Cart | Remove Item | L | 1 | L | 1 | 1 | 0 | 1 | 1 | Simple operation; minimal dependencies | 14
7 | Checkout | Credit Card Payment | H | 5 | H | 5 | 25 | 0 | 25 | 3 | Payment gateway; PCI; high revenue impact | 3
8 | Checkout | Guest Checkout | H | 5 | H | 5 | 25 | 0 | 25 | 2.5 | Alternative path; less tested | 4
9 | Checkout | Coupon Codes | M | 3 | L | 1 | 3 | 0 | 3 | 2 | Business logic complexity; low impact | 11
10 | Checkout | Tax Calculation | L | 1 | H | 5 | 5 | 0 | 5 | 2 | Mature engine; regulatory implications | 8
11 | Notifications | Order Confirmation Email | M | 3 | M | 3 | 9 | 0 | 9 | 1 | Email service; template rendering | 7
12 | Notifications | Shipping Notifications | L | 1 | L | 1 | 1 | 0 | 1 | 1 | Third-party API; informational only | 15
13 | User Admin | User Registration | M | 3 | H | 5 | 15 | 0 | 15 | 1.5 | New user onboarding; data integrity | 5
14 | User Admin | Profile Management | L | 1 | L | 1 | 1 | 0 | 1 | 0.5 | Simple CRUD; low traffic | 16
15 | Reporting | Sales Reports | L | 1 | M | 3 | 3 | 0 | 3 | 1 | Read-only; accuracy matters | 12
16 | Reporting | Inventory Reports | L | 1 | M | 3 | 3 | 0 | 3 | 1 | Backend reporting; operational visibility | 13
[9 empty] | Total: | 26.5 | hours (estimated execution time)
Enter H/M/L in Likelihood and Impact. Adjust (+/-) lets you manually bump priority for individual items — use it to break ties or override the computed ranking. The Planning View sorts by Effective Priority.

## Planning View
Planning View — Sorted by Effective Priority
Inputs: |  | # Testers: | 1 | Hrs/Tester/Day: | 5 | Start Date: | 2026-06-01 | End Date: | 2026-06-05
Capacity: | 5 | business days | 25 | hours available |  | Coverage: | 14 | of 16 items
# | Objective | Inventory | Likelihood | Impact | Priority | Adjust | Eff. Priority | Est. Hours | Cum. Hours | Status
1 | Authentication | Login / Logout | H | H | 25 | 0 | 25 | 3 | 3 | Test this cycle
2 | Shopping Cart | Add to Cart | H | H | 25 | 0 | 25 | 3 | 6 | Test this cycle
3 | Checkout | Credit Card Payment | H | H | 25 | 0 | 25 | 3 | 9 | Test this cycle
4 | Checkout | Guest Checkout | H | H | 25 | 0 | 25 | 2.5 | 11.5 | Test this cycle
5 | User Admin | User Registration | M | H | 15 | 0 | 15 | 1.5 | 13 | Test this cycle
6 | Authentication | Password Reset | M | M | 9 | 0 | 9 | 2 | 15 | Test this cycle
7 | Notifications | Order Confirmation Email | M | M | 9 | 0 | 9 | 1 | 16 | Test this cycle
8 | Checkout | Tax Calculation | L | H | 5 | 0 | 5 | 2 | 18 | Test this cycle
9 | Authentication | Session Timeout | L | M | 3 | 0 | 3 | 1 | 19 | Test this cycle
10 | Shopping Cart | Update Quantity | L | M | 3 | 0 | 3 | 1 | 20 | Test this cycle
11 | Checkout | Coupon Codes | M | L | 3 | 0 | 3 | 2 | 22 | Test this cycle
12 | Reporting | Sales Reports | L | M | 3 | 0 | 3 | 1 | 23 | Test this cycle
13 | Reporting | Inventory Reports | L | M | 3 | 0 | 3 | 1 | 24 | Test this cycle
14 | Shopping Cart | Remove Item | L | L | 1 | 0 | 1 | 1 | 25 | Test this cycle
15 | Notifications | Shipping Notifications | L | L | 1 | 0 | 1 | 1 | 26 | At capacity
16 | User Admin | Profile Management | L | L | 1 | 0 | 1 | 0.5 | 26.5 | Deferred
[7 empty] | Total: | 26.5 | total hours | Above cut-line:
Above cut-line: 25.0 hours of 25.0 available ¦ Adjust planning inputs (amber cells) or Adjust (+/-) values on Risk Analysis sheet to change the cut-line.

## Template
Risk Analysis Template
Copy this sheet for new projects. Enter objectives, inventories, and H/M/L ratings.
[6 empty] | Scoring Key: | H = 5 | M = 3 | L = 1
# | Objective | Inventory | Likelihood | L Score | Impact | I Score | Priority | Adjust (+/-) | Eff. Priority | Est. Hours | Notes / Rationale
1 | [7 empty] | 0
2 | [7 empty] | 0
3 | [7 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
[9 empty] | Total: | 0
Adjust (+/-) lets you manually bump priority for individual items to break ties or override computed ranking. Est. Hours is optional.